**Project Status Report III**

|  |
| --- |
| Date of Report Issue/Prepared: Mar 18,2020 |

Report Prepared By:

Katiuscia Novaes De Sa, Viacheslav Nepomniashchyi,

Aregawi Gebremichaeal, Hussein Kalifa.

Employer/Organization: George Brown College

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | GBC Event Management System | |
| T05 | |
| Start Date: Feb. 2**, 2020** | End Date: March 18**, 2020** |
| Yellow (Warning) - Most tasks completed as planned. | |

Summary

|  |
| --- |
| **Project Status Summary** |
| Use -cases are mostly implemented and tested.  Basic version of the App has been installed on the production server. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| User registration and login cases are implemented | Admin dashboard functionality is still in process |
| Event creation and editing finished | Authorization process flag is still off and feature is not tested. Algorithm of email domain defining is not coded. |
| Commenting on Event Page is added. | Bootstrap is not fully implemented on the blade templates. |
| Navigation menu for Admin page is coded. |  |
| Font awesome icons are added across the pages. |  |

Upcoming Objectives for March 18, 2020, 2020 to March 27, 2020

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To | | Duration | Date |
| Admin table development and migration wiring. | HK | | 5 days | Mar.18 to Mar.23 |
| Searching and displaying events. | AG | | 3 days | Mar.18 to Mar.21 |
| User authentication procedure implementation. | AG | | 3 days | Mar.21 to Mar.24 |
| Admin dashboard functionality coding and wiring | VN | | 6 days | Mar.18 to Mar.24 |
| Bootstrap and Font awesome polishing | KN | | 3 days | Mar.21 to Mar.24 |
| Testing App’s functionality, integrity, cases, stability. | KN | | 3 days | Mar.24 to Mar.27 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| **Milestone (Objective)** | | **Assigned To** | **Delivery Date** |
| Finish coding part. Provide throughout testing. Debug and deploy the finalized app. | | KN, VN, AG, HK | March 27 |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Event, user, comment status are being changed manually instead of the functions. | Adjust and wire admin functions to db, test them. | March 25 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| File uploading-downloading on the Event Page. | Med | Med | Search for an implementation for the earlier versions of the framework, twit and test it for Laravel 5.8. |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport3”.

For e.g. T36\_ProjectStatusReport3

This is a group submission i.e. one per group.

**Due Dates:**

**Wednesday, March 18, 2020 (11:59 p.m.)**